## Product Backlog
Key | Type | Parent Epic | Summary | Story Points | Priority | Status | Sprint | Label | Component(s) | Fix Version | Assignee
CIRRS-1 | Epic |  | User Management & Authentication |  | Medium | To Do | Backlog | User-Admin | Backend-API, Database | Version 1.0 | Anish K V
CIRRS-2 | Epic |  | Citizen Issue Reporting |  | Medium | To Do | Backlog | Citizen | Backend-API, Mobile-App | Version 1.0 | Anish K V
CIRRS-3 | Epic |  | Municipal Triage & Verification |  | Medium | To Do | Backlog | Staff | Backend-API, Web-Portal | Version 2.0 | Balaji M
CIRRS-4 | Epic |  | Department Assignment & Resolution |  | Medium | To Do | Backlog | Officer | Backend-API, Web-Portal | Version 2.0 | Balaji M
CIRRS-5 | Epic |  | Notifications & Status Tracking |  | Medium | To Do | Backlog | Notification | Mobile-App, Notification-Service | Version 3.0 | Anish K V
CIRRS-6 | Epic |  | Admin Dashboard & Reporting |  | Medium | To Do | Backlog | Admin | Database, Web-Portal | Version 3.0 | Balaji M
CIRRS-7 | Story | CIRRS-1 - User Management & Authentication | As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | 5 | High | Done | Sprint 1 | User-Admin | Backend-API, Mobile-App | Version 1.0 | Anish K V
CIRRS-8 | Story | CIRRS-1 - User Management & Authentication | As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | 3 | High | Done | Sprint 1 | User-Admin | Backend-API, Mobile-App | Version 1.0 | Anish K V
CIRRS-9 | Story | CIRRS-1 - User Management & Authentication | As a user, I want to reset my password when I forget it, so that I can regain access to my account. | 3 | Medium | To Do | Sprint 1 | User-Admin | Backend-API, Notification-Service | Version 1.0 | Anish K V
CIRRS-10 | Story | CIRRS-1 - User Management & Authentication | As a user, I want to view and update my profile details, so that my contact information stays current. | 3 | Low | To Do | Sprint 2 | User-Admin | Backend-API, Mobile-App | Version 1.0 | Anish K V
CIRRS-11 | Story | CIRRS-1 - User Management & Authentication | As an administrator, I want role-based access control for citizens, staff and officers, so that each user only sees what they are permitted to. | 8 | High | To Do | Sprint 2 | User-Admin | Backend-API, Database | Version 1.0 | Anish K V
CIRRS-12 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | 5 | High | Done | Sprint 1 | Citizen | Mobile-App | Version 1.0 | Anish K V
CIRRS-13 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | 8 | High | In Progress | Sprint 1 | Citizen | Backend-API, Mobile-App | Version 1.0 | Anish K V
CIRRS-14 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to select a category for my issue, so that it reaches the correct department faster. | 3 | Medium | To Do | Sprint 1 | Citizen | Database, Mobile-App | Version 1.0 | Anish K V
CIRRS-15 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to add a text description to my report, so that I can explain details the photo does not show. | 2 | Medium | To Do | Sprint 1 | Citizen | Mobile-App | Version 1.0 | Anish K V
CIRRS-16 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | 5 | High | In Review | Sprint 1 | Citizen | Backend-API, Database, Mobile-App | Version 1.0 | Anish K V
CIRRS-17 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to see validation errors before submitting, so that I can correct an incomplete report. | 2 | Low | To Do | Sprint 2 | Citizen | Mobile-App | Version 1.0 | Anish K V
CIRRS-18 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to see a queue of newly submitted reports, so that I can review them promptly. | 5 | High | To Do | Sprint 2 | Staff | Backend-API, Web-Portal | Version 2.0 | Balaji M
CIRRS-19 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to verify a report against its photo and location, so that I can confirm it is genuine. | 5 | High | To Do | Sprint 2 | Staff | Web-Portal | Version 2.0 | Balaji M
CIRRS-20 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to reject fake or duplicate reports with a reason, so that departments are not burdened with invalid work. | 3 | Medium | To Do | Sprint 2 | Staff | Notification-Service, Web-Portal | Version 2.0 | Balaji M
CIRRS-21 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to assign a verified report to the correct department, so that the right team resolves it. | 8 | High | To Do | Sprint 2 | Staff | Backend-API, Web-Portal | Version 2.0 | Balaji M
CIRRS-22 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to set a priority on each report, so that urgent hazards are handled first. | 3 | Medium | To Do | Sprint 2 | Staff | Web-Portal | Version 2.0 | Balaji M
CIRRS-23 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to view all issues assigned to my department, so that I can plan my field work. | 5 | High | To Do | Sprint 2 | Officer | Backend-API, Web-Portal | Version 2.0 | Balaji M
CIRRS-24 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to accept an assigned task, so that the citizen knows work has begun. | 3 | High | To Do | Sprint 2 | Officer | Notification-Service, Web-Portal | Version 2.0 | Balaji M
CIRRS-25 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to update work progress on an issue, so that the status stays accurate. | 3 | Medium | To Do | Sprint 2 | Officer | Web-Portal | Version 2.0 | Balaji M
CIRRS-26 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to upload a resolution photo as proof of completion, so that the citizen can see the issue was fixed. | 8 | High | To Do | Sprint 3 | Officer | Backend-API, Web-Portal | Version 3.0 | Balaji M
CIRRS-27 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to reassign an issue to another department, so that misrouted issues reach the right team. | 5 | Medium | To Do | Sprint 3 | Officer | Web-Portal | Version 3.0 | Balaji M
CIRRS-28 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to receive a notification when my report status changes, so that I stay informed without checking the app. | 5 | High | To Do | Sprint 3 | Notification | Mobile-App, Notification-Service | Version 3.0 | Anish K V
CIRRS-29 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to track the current status of my report in the app, so that I know what stage it is at. | 5 | High | To Do | Sprint 3 | Notification | Backend-API, Mobile-App | Version 3.0 | Anish K V
CIRRS-30 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to view the resolution proof photo, so that I can confirm the issue was actually fixed. | 3 | Medium | To Do | Sprint 3 | Notification | Mobile-App | Version 3.0 | Anish K V
CIRRS-31 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to reopen a resolved issue if the problem persists, so that it gets proper attention. | 5 | Medium | To Do | Sprint 3 | Notification | Backend-API, Mobile-App | Version 3.0 | Anish K V
CIRRS-32 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to manage departments and their officers, so that routing rules stay accurate. | 5 | Medium | To Do | Sprint 3 | Admin | Database, Web-Portal | Version 3.0 | Balaji M
CIRRS-33 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to manage user accounts and deactivate abusive reporters, so that the platform stays trustworthy. | 5 | Medium | To Do | Sprint 3 | Admin | Backend-API, Web-Portal | Version 3.0 | Balaji M
CIRRS-34 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to generate reports on issue volume and resolution time, so that I can measure departmental performance. | 8 | High | To Do | Sprint 3 | Admin | Database, Web-Portal | Version 3.0 | Balaji M
CIRRS-35 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to monitor a live map of open issues, so that I can spot problem hotspots in the city. | 8 | Medium | To Do | Sprint 3 | Admin | Web-Portal | Version 3.0 | Balaji M
CIRRS-36 | Task | CIRRS-1 - User Management & Authentication | Set up Git repository, branching strategy and CI pipeline |  | High | Done | Sprint 1 | Technical-Task | Backend-API | Version 1.0 | Anish K V
CIRRS-37 | Task | CIRRS-1 - User Management & Authentication | Design the database schema for users, issues, departments and resolutions |  | High | Done | Sprint 1 | Technical-Task | Database | Version 1.0 | Anish K V
CIRRS-38 | Task | CIRRS-2 - Citizen Issue Reporting | Prepare UI/UX wireframes for the citizen mobile app |  | Medium | Done | Sprint 1 | Technical-Task | Mobile-App | Version 1.0 | Anish K V
CIRRS-39 | Task | CIRRS-2 - Citizen Issue Reporting | Register and configure GPS / Map service API keys and quotas |  | Medium | To Do | Sprint 2 | Technical-Task | Mobile-App | Version 1.0 | Anish K V
CIRRS-40 | Task | CIRRS-3 - Municipal Triage & Verification | Write the system test plan and acceptance criteria checklist |  | Medium | To Do | Sprint 2 | Technical-Task | Web-Portal | Version 2.0 | Balaji M
CIRRS-41 | Task | CIRRS-6 - Admin Dashboard & Reporting | Prepare the user training guide for municipal staff and officers |  | Low | To Do | Sprint 3 | Technical-Task | Web-Portal | Version 3.0 | Balaji M
CIRRS-42 | Bug | CIRRS-2 - Citizen Issue Reporting | BUG: GPS coordinates drift by up to 200 m when a report is created indoors |  | High | In Progress | Sprint 1 | Defect | Mobile-App | Version 1.0 | Anish K V
CIRRS-43 | Bug | CIRRS-2 - Citizen Issue Reporting | BUG: Photo upload fails silently when the image is larger than 5 MB |  | High | To Do | Sprint 1 | Defect | Mobile-App | Version 1.0 | Anish K V
CIRRS-44 | Bug | CIRRS-5 - Notifications & Status Tracking | BUG: Status-change notification is delivered twice when an officer updates progress rapidly |  | Medium | To Do | Backlog | Defect | Notification-Service | Version 3.0 | Anish K V
CIRRS-45 | Bug | CIRRS-3 - Municipal Triage & Verification | BUG: Rejected reports still appear in the department officer queue |  | Medium | To Do | Backlog | Defect | Web-Portal | Version 2.0 | Balaji M

## Sprint 1 Backlog
Key | Type | Parent | Summary | Story Points | Priority | Status | Assignee
CIRRS-7 | Story | CIRRS-1 - User Management & Authentication | As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | 5 | High | Done | Anish K V
CIRRS-8 | Story | CIRRS-1 - User Management & Authentication | As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | 3 | High | Done | Anish K V
CIRRS-9 | Story | CIRRS-1 - User Management & Authentication | As a user, I want to reset my password when I forget it, so that I can regain access to my account. | 3 | Medium | To Do | Anish K V
CIRRS-12 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | 5 | High | Done | Anish K V
CIRRS-13 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | 8 | High | In Progress | Anish K V
CIRRS-14 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to select a category for my issue, so that it reaches the correct department faster. | 3 | Medium | To Do | Anish K V
CIRRS-15 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to add a text description to my report, so that I can explain details the photo does not show. | 2 | Medium | To Do | Anish K V
CIRRS-16 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | 5 | High | In Review | Anish K V
CIRRS-36 | Task | CIRRS-1 - User Management & Authentication | Set up Git repository, branching strategy and CI pipeline |  | High | Done | Anish K V
CIRRS-37 | Task | CIRRS-1 - User Management & Authentication | Design the database schema for users, issues, departments and resolutions |  | High | Done | Anish K V
CIRRS-38 | Task | CIRRS-2 - Citizen Issue Reporting | Prepare UI/UX wireframes for the citizen mobile app |  | Medium | Done | Anish K V
CIRRS-42 | Bug | CIRRS-2 - Citizen Issue Reporting | BUG: GPS coordinates drift by up to 200 m when a report is created indoors |  | High | In Progress | Anish K V
CIRRS-43 | Bug | CIRRS-2 - Citizen Issue Reporting | BUG: Photo upload fails silently when the image is larger than 5 MB |  | High | To Do | Anish K V
CIRRS-46 | Sub-task | CIRRS-7 - As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | Design the registration screen mockup and field validation rules |  | Medium | Done | Anish K V
CIRRS-47 | Sub-task | CIRRS-7 - As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | Write the technical implementation strategy for OTP verification |  | Medium | Done | Anish K V
CIRRS-48 | Sub-task | CIRRS-7 - As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | Create the registration user interface layout in the mobile app |  | Medium | Done | Anish K V
CIRRS-49 | Sub-task | CIRRS-7 - As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | Write unit tests and code for the registration API endpoint |  | Medium | Done | Anish K V
CIRRS-50 | Sub-task | CIRRS-7 - As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | Integrate the SMS gateway for OTP delivery |  | Medium | Done | Anish K V
CIRRS-51 | Sub-task | CIRRS-7 - As a citizen, I want to register with my phone number and email, so that I can start reporting civic issues in my area. | Write and run acceptance tests for the registration flow |  | Medium | Done | Anish K V
CIRRS-52 | Sub-task | CIRRS-8 - As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | Design the login screen mockup |  | Medium | Done | Anish K V
CIRRS-53 | Sub-task | CIRRS-8 - As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | Implement JWT session token issue and refresh on the back end |  | Medium | Done | Anish K V
CIRRS-54 | Sub-task | CIRRS-8 - As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | Write unit tests and code for the login API endpoint |  | Medium | Done | Anish K V
CIRRS-55 | Sub-task | CIRRS-8 - As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | Implement account lockout after five failed attempts |  | Medium | Done | Anish K V
CIRRS-56 | Sub-task | CIRRS-8 - As a registered user, I want to log in securely with my credentials, so that I can access my account and reports. | Write and run acceptance tests for the login flow |  | Medium | Done | Anish K V
CIRRS-57 | Sub-task | CIRRS-9 - As a user, I want to reset my password when I forget it, so that I can regain access to my account. | Design the forgot-password and reset password screens |  | Medium | To Do | Anish K V
CIRRS-58 | Sub-task | CIRRS-9 - As a user, I want to reset my password when I forget it, so that I can regain access to my account. | Implement time-limited reset token generation and expiry |  | Medium | To Do | Anish K V
CIRRS-59 | Sub-task | CIRRS-9 - As a user, I want to reset my password when I forget it, so that I can regain access to my account. | Build the password-reset email template |  | Medium | To Do | Anish K V
CIRRS-60 | Sub-task | CIRRS-9 - As a user, I want to reset my password when I forget it, so that I can regain access to my account. | Write unit tests and code for the reset endpoints |  | Medium | To Do | Anish K V
CIRRS-61 | Sub-task | CIRRS-9 - As a user, I want to reset my password when I forget it, so that I can regain access to my account. | Write and run acceptance tests for password reset |  | Medium | To Do | Anish K V
CIRRS-62 | Sub-task | CIRRS-12 - As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | Create the camera and gallery picker user interface layout |  | Medium | Done | Anish K V
CIRRS-63 | Sub-task | CIRRS-12 - As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | Implement runtime camera permission handling |  | Medium | Done | Anish K V
CIRRS-64 | Sub-task | CIRRS-12 - As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | Implement client-side image compression to under 2 MB |  | Medium | Done | Anish K V
CIRRS-65 | Sub-task | CIRRS-12 - As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | Write unit tests for the photo attachment component |  | Medium | Done | Anish K V
CIRRS-66 | Sub-task | CIRRS-12 - As a citizen, I want to capture a photo of a civic issue from within the app, so that I can provide visual evidence of the problem. | Run acceptance tests for photo capture on Android and iOS |  | Medium | Done | Anish K V
CIRRS-67 | Sub-task | CIRRS-13 - As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | Write the technical implementation strategy for GPS capture and reverse geocoding |  | Medium | Done | Anish K V
CIRRS-68 | Sub-task | CIRRS-13 - As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | Implement runtime location permission handling with a rationale dialog |  | Medium | In Progress | Anish K V
CIRRS-69 | Sub-task | CIRRS-13 - As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | Integrate the map SDK and the draggable confirmation pin |  | Medium | In Progress | Anish K V
CIRRS-70 | Sub-task | CIRRS-13 - As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | Implement reverse geocoding to a human-readable address |  | Medium | Done | Anish K V
CIRRS-71 | Sub-task | CIRRS-13 - As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | Handle GPS-unavailable and permission-denied states |  | Medium | Done | Anish K V
CIRRS-72 | Sub-task | CIRRS-13 - As a citizen, I want the app to auto-detect my GPS location when I report an issue, so that the issue is geotagged accurately. | Write and run acceptance tests for location capture accuracy |  | Medium | To Do | Anish K V
CIRRS-73 | Sub-task | CIRRS-14 - As a citizen, I want to select a category for my issue, so that it reaches the correct department faster. | Create the category master table and seed the initial data |  | Medium | To Do | Anish K V
CIRRS-74 | Sub-task | CIRRS-14 - As a citizen, I want to select a category for my issue, so that it reaches the correct department faster. | Build the category list API endpoint |  | Medium | To Do | Anish K V
CIRRS-75 | Sub-task | CIRRS-14 - As a citizen, I want to select a category for my issue, so that it reaches the correct department faster. | Create the category selection user interface layout |  | Medium | To Do | Anish K V
CIRRS-76 | Sub-task | CIRRS-14 - As a citizen, I want to select a category for my issue, so that it reaches the correct department faster. | Write unit tests for the category-to-department mapping |  | Medium | To Do | Anish K V
CIRRS-77 | Sub-task | CIRRS-15 - As a citizen, I want to add a text description to my report, so that I can explain details the photo does not show. | Create the description input layout with a live character counter |  | Medium | To Do | Anish K V
CIRRS-78 | Sub-task | CIRRS-15 - As a citizen, I want to add a text description to my report, so that I can explain details the photo does not show. | Implement trimming and 500-character server-side validation |  | Medium | To Do | Anish K V
CIRRS-79 | Sub-task | CIRRS-15 - As a citizen, I want to add a text description to my report, so that I can explain details the photo does not show. | Integrate the profanity flagging check |  | Medium | To Do | Anish K V
CIRRS-80 | Sub-task | CIRRS-15 - As a citizen, I want to add a text description to my report, so that I can explain details the photo does not show. | Write unit tests for description validation |  | Medium | To Do | Anish K V
CIRRS-81 | Sub-task | CIRRS-16 - As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | Design the submission confirmation screen mockup |  | Medium | Done | Anish K V
CIRRS-82 | Sub-task | CIRRS-16 - As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | Implement the transactional report-creation API endpoint |  | Medium | Done | Anish K V
CIRRS-83 | Sub-task | CIRRS-16 - As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | Implement reference ID generation and uniqueness check |  | Medium | Done | Anish K V
CIRRS-84 | Sub-task | CIRRS-16 - As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | Build the offline submission queue and retry mechanism |  | Medium | Done | Anish K V
CIRRS-85 | Sub-task | CIRRS-16 - As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | Write unit tests and code for the report persistence layer |  | Medium | In Progress | Anish K V
CIRRS-90 | Sub-task | CIRRS-16 - As a citizen, I want to submit my report and receive a reference ID, so that I can track its progress later. | Write and run acceptance tests for end-to-end submission |  | Medium | In Progress | Anish K V

## Sprint 2 Backlog
Key | Type | Parent | Summary | Story Points | Priority | Status | Assignee
CIRRS-10 | Story | CIRRS-1 - User Management & Authentication | As a user, I want to view and update my profile details, so that my contact information stays current. | 3 | Low | To Do | Anish K V
CIRRS-11 | Story | CIRRS-1 - User Management & Authentication | As an administrator, I want role-based access control for citizens, staff and officers, so that each user only sees what they are permitted to. | 8 | High | To Do | Anish K V
CIRRS-17 | Story | CIRRS-2 - Citizen Issue Reporting | As a citizen, I want to see validation errors before submitting, so that I can correct an incomplete report. | 2 | Low | To Do | Anish K V
CIRRS-18 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to see a queue of newly submitted reports, so that I can review them promptly. | 5 | High | To Do | Balaji M
CIRRS-19 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to verify a report against its photo and location, so that I can confirm it is genuine. | 5 | High | To Do | Balaji M
CIRRS-20 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to reject fake or duplicate reports with a reason, so that departments are not burdened with invalid work. | 3 | Medium | To Do | Balaji M
CIRRS-21 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to assign a verified report to the correct department, so that the right team resolves it. | 8 | High | To Do | Balaji M
CIRRS-22 | Story | CIRRS-3 - Municipal Triage & Verification | As municipal staff, I want to set a priority on each report, so that urgent hazards are handled first. | 3 | Medium | To Do | Balaji M
CIRRS-23 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to view all issues assigned to my department, so that I can plan my field work. | 5 | High | To Do | Balaji M
CIRRS-24 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to accept an assigned task, so that the citizen knows work has begun. | 3 | High | To Do | Balaji M
CIRRS-25 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to update work progress on an issue, so that the status stays accurate. | 3 | Medium | To Do | Balaji M
CIRRS-39 | Task | CIRRS-2 - Citizen Issue Reporting | Register and configure GPS / Map service API keys and quotas |  | Medium | To Do | Anish K V
CIRRS-40 | Task | CIRRS-3 - Municipal Triage & Verification | Write the system test plan and acceptance criteria checklist |  | Medium | To Do | Balaji M
CIRRS-86 | Sub-task | CIRRS-18 - As municipal staff, I want to see a queue of newly submitted reports, so that I can review them promptly. | Build the new-report queue table view with photo thumbnails |  | Medium | To Do | Balaji M
CIRRS-87 | Sub-task | CIRRS-18 - As municipal staff, I want to see a queue of newly submitted reports, so that I can review them promptly. | Implement queue filtering by category, ward and date range |  | Medium | To Do | Balaji M
CIRRS-88 | Sub-task | CIRRS-18 - As municipal staff, I want to see a queue of newly submitted reports, so that I can review them promptly. | Implement pagination and 60-second auto-refresh |  | Medium | To Do | Balaji M
CIRRS-89 | Sub-task | CIRRS-18 - As municipal staff, I want to see a queue of newly submitted reports, so that I can review them promptly. | Write and run acceptance tests for the new-report queue |  | Medium | To Do | Balaji M
CIRRS-105 | Sub-task | CIRRS-19 - As municipal staff, I want to verify a report against its photo and location, so that I can confirm it is genuine. | Build the report detail view with full-size photo and map pin |  | Medium | To Do | Balaji M
CIRRS-100 | Sub-task | CIRRS-19 - As municipal staff, I want to verify a report against its photo and location, so that I can confirm it is genuine. | Implement the 100 m duplicate-proximity query |  | Medium | To Do | Balaji M
CIRRS-99 | Sub-task | CIRRS-19 - As municipal staff, I want to verify a report against its photo and location, so that I can confirm it is genuine. | Implement the Verify action and its status transition |  | Medium | To Do | Balaji M
CIRRS-106 | Sub-task | CIRRS-19 - As municipal staff, I want to verify a report against its photo and location, so that I can confirm it is genuine. | Write and run acceptance tests for report verification |  | Medium | To Do | Balaji M
CIRRS-91 | Sub-task | CIRRS-20 - As municipal staff, I want to reject fake or duplicate reports with a reason, so that departments are not burdened with invalid work. | Create the rejection reason master list and seed data |  | Medium | To Do | Balaji M
CIRRS-95 | Sub-task | CIRRS-20 - As municipal staff, I want to reject fake or duplicate reports with a reason, so that departments are not burdened with invalid work. | Build the rejection dialog with reason and free-text note |  | Medium | To Do | Balaji M
CIRRS-97 | Sub-task | CIRRS-20 - As municipal staff, I want to reject fake or duplicate reports with a reason, so that departments are not burdened with invalid work. | Implement the Rejected transition and citizen notification |  | Medium | To Do | Balaji M
CIRRS-98 | Sub-task | CIRRS-20 - As municipal staff, I want to reject fake or duplicate reports with a reason, so that departments are not burdened with invalid work. | Write unit tests for excluding rejected reports from department queues |  | Medium | To Do | Balaji M
CIRRS-93 | Sub-task | CIRRS-21 - As municipal staff, I want to assign a verified report to the correct department, so that the right team resolves it. | Implement the category-to-department auto-suggestion rules |  | Medium | To Do | Balaji M
CIRRS-108 | Sub-task | CIRRS-21 - As municipal staff, I want to assign a verified report to the correct department, so that the right team resolves it. | Build the department override selector in the web portal |  | Medium | To Do | Balaji M
CIRRS-102 | Sub-task | CIRRS-21 - As municipal staff, I want to assign a verified report to the correct department, so that the right team resolves it. | Implement the assignment API and status transition |  | Medium | To Do | Balaji M
CIRRS-96 | Sub-task | CIRRS-21 - As municipal staff, I want to assign a verified report to the correct department, so that the right team resolves it. | Record the assignment history against the report |  | Medium | To Do | Balaji M
CIRRS-103 | Sub-task | CIRRS-22 - As municipal staff, I want to set a priority on each report, so that urgent hazards are handled first. | Add the priority selector to the report detail view |  | Medium | To Do | Balaji M
CIRRS-107 | Sub-task | CIRRS-22 - As municipal staff, I want to set a priority on each report, so that urgent hazards are handled first. | Enforce a justification note when Critical priority is chosen |  | Medium | To Do | Balaji M
CIRRS-109 | Sub-task | CIRRS-22 - As municipal staff, I want to set a priority on each report, so that urgent hazards are handled first. | Implement department queue sorting by priority then age |  | Medium | To Do | Balaji M
CIRRS-110 | Sub-task | CIRRS-22 - As municipal staff, I want to set a priority on each report, so that urgent hazards are handled first. | Write priority change entries into the audit log |  | Medium | To Do | Balaji M
CIRRS-111 | Sub-task | CIRRS-24 - As a department officer, I want to accept an assigned task, so that the citizen knows work has begun. | Build the Accept action on the officer issue view |  | Medium | To Do | Balaji M
CIRRS-112 | Sub-task | CIRRS-24 - As a department officer, I want to accept an assigned task, so that the citizen knows work has begun. | Implement the In Progress transition with officer attribution |  | Medium | To Do | Balaji M
CIRRS-113 | Sub-task | CIRRS-24 - As a department officer, I want to accept an assigned task, so that the citizen knows work has begun. | Add the expected completion date field to the accept dialog |  | Medium | To Do | Balaji M
CIRRS-114 | Sub-task | CIRRS-24 - As a department officer, I want to accept an assigned task, so that the citizen knows work has begun. | Implement the 48-hour unaccepted issue flag |  | Medium | To Do | Balaji M
CIRRS-115 | Sub-task | CIRRS-25 - As a department officer, I want to update work progress on an issue, so that the status stays accurate. | Build the progress note form with an optional photo attachment |  | Medium | To Do | Balaji M
CIRRS-116 | Sub-task | CIRRS-25 - As a department officer, I want to update work progress on an issue, so that the status stays accurate. | Make progress notes immutable once saved |  | Medium | To Do | Balaji M
CIRRS-117 | Sub-task | CIRRS-25 - As a department officer, I want to update work progress on an issue, so that the status stays accurate. | Surface the latest progress note in the citizen app |  | Medium | To Do | Balaji M
CIRRS-118 | Sub-task | CIRRS-25 - As a department officer, I want to update work progress on an issue, so that the status stays accurate. | Write and run acceptance tests for progress updates |  | Medium | To Do | Balaji M

## Sprint 3 Backlog
Key | Type | Parent | Summary | Story Points | Priority | Status | Assignee
CIRRS-26 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to upload a resolution photo as proof of completion, so that the citizen can see the issue was fixed. | 8 | High | To Do | Balaji M
CIRRS-27 | Story | CIRRS-4 - Department Assignment & Resolution | As a department officer, I want to reassign an issue to another department, so that misrouted issues reach the right team. | 5 | Medium | To Do | Balaji M
CIRRS-28 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to receive a notification when my report status changes, so that I stay informed without checking the app. | 5 | High | To Do | Anish K V
CIRRS-29 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to track the current status of my report in the app, so that I know what stage it is at. | 5 | High | To Do | Anish K V
CIRRS-30 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to view the resolution proof photo, so that I can confirm the issue was actually fixed. | 3 | Medium | To Do | Anish K V
CIRRS-31 | Story | CIRRS-5 - Notifications & Status Tracking | As a citizen, I want to reopen a resolved issue if the problem persists, so that it gets proper attention. | 5 | Medium | To Do | Anish K V
CIRRS-32 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to manage departments and their officers, so that routing rules stay accurate. | 5 | Medium | To Do | Balaji M
CIRRS-33 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to manage user accounts and deactivate abusive reporters, so that the platform stays trustworthy. | 5 | Medium | To Do | Balaji M
CIRRS-34 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to generate reports on issue volume and resolution time, so that I can measure departmental performance. | 8 | High | To Do | Balaji M
CIRRS-35 | Story | CIRRS-6 - Admin Dashboard & Reporting | As an administrator, I want to monitor a live map of open issues, so that I can spot problem hotspots in the city. | 8 | Medium | To Do | Balaji M
CIRRS-41 | Task | CIRRS-6 - Admin Dashboard & Reporting | Prepare the user training guide for municipal staff and officers |  | Low | To Do | Balaji M
CIRRS-101 | Sub-task | CIRRS-26 - As a department officer, I want to upload a resolution photo as proof of completion, so that the citizen can see the issue was fixed. | Build the resolution photo upload interface for department officers |  | Medium | To Do | Balaji M
CIRRS-94 | Sub-task | CIRRS-26 - As a department officer, I want to upload a resolution photo as proof of completion, so that the citizen can see the issue was fixed. | Implement resolution photo storage and completion-date capture |  | Medium | To Do | Balaji M
CIRRS-104 | Sub-task | CIRRS-26 - As a department officer, I want to upload a resolution photo as proof of completion, so that the citizen can see the issue was fixed. | Implement the Resolved status transition and notification trigger |  | Medium | To Do | Balaji M
CIRRS-92 | Sub-task | CIRRS-26 - As a department officer, I want to upload a resolution photo as proof of completion, so that the citizen can see the issue was fixed. | Write and run acceptance tests for the resolution flow |  | Medium | To Do | Balaji M
CIRRS-119 | Sub-task | CIRRS-28 - As a citizen, I want to receive a notification when my report status changes, so that I stay informed without checking the app. | Integrate the push notification provider SDK |  | Medium | To Do | Anish K V
CIRRS-120 | Sub-task | CIRRS-28 - As a citizen, I want to receive a notification when my report status changes, so that I stay informed without checking the app. | Implement notification retry logic with a maximum of three attempts |  | Medium | To Do | Anish K V
CIRRS-121 | Sub-task | CIRRS-28 - As a citizen, I want to receive a notification when my report status changes, so that I stay informed without checking the app. | Build the per-report notification mute setting |  | Medium | To Do | Anish K V

## Summary
Civic/Community Issue Reporting & Routing System - Scrum Summary
Jira project key | CIRRS
Jira site | https://anlietyt.atlassian.net
Board | CIRRS board (Scrum, company-managed)
Team | Anish K V (CB.EN.U4CCE24005), Balaji M (CB.EN.U4CCE24010)
Workflow | To Do -> In Progress -> In Review -> Done
Work items by type
Issue type | Count
Epic | 6
Story | 29
Task | 6
Bug | 4
Sub-task | 76
Total | 121
Work items by status
Status | Count
To Do | 85
In Progress | 6
In Review | 1
Done | 29
Sprint allocation and velocity
Sprint | Items | Story points committed | Points completed | % points complete
Sprint 1 | 54 | 34 | 13 | 38.24%
Sprint 2 | 41 | 48 | 0 | 0%
Sprint 3 | 18 | 57 | 0 | 0%
Backlog | 8 | 0 | 0 | 0%
Workload by team member
Assignee | Items assigned | Story points
Anish K V | 69 | 65
Balaji M | 52 | 74
Note: all figures are live formulas over the Data sheet, which holds the export of every Jira work item in project CIRRS as at 30 Aug 2026.

## Data (hidden)
Key | Type | Status | Sprint | Points | Assignee
CIRRS-1 | Epic | To Do | Backlog |  | Anish K V
CIRRS-2 | Epic | To Do | Backlog |  | Anish K V
CIRRS-3 | Epic | To Do | Backlog |  | Balaji M
CIRRS-4 | Epic | To Do | Backlog |  | Balaji M
CIRRS-5 | Epic | To Do | Backlog |  | Anish K V
CIRRS-6 | Epic | To Do | Backlog |  | Balaji M
CIRRS-7 | Story | Done | Sprint 1 | 5 | Anish K V
CIRRS-8 | Story | Done | Sprint 1 | 3 | Anish K V
CIRRS-9 | Story | To Do | Sprint 1 | 3 | Anish K V
CIRRS-10 | Story | To Do | Sprint 2 | 3 | Anish K V
CIRRS-11 | Story | To Do | Sprint 2 | 8 | Anish K V
CIRRS-12 | Story | Done | Sprint 1 | 5 | Anish K V
CIRRS-13 | Story | In Progress | Sprint 1 | 8 | Anish K V
CIRRS-14 | Story | To Do | Sprint 1 | 3 | Anish K V
CIRRS-15 | Story | To Do | Sprint 1 | 2 | Anish K V
CIRRS-16 | Story | In Review | Sprint 1 | 5 | Anish K V
CIRRS-17 | Story | To Do | Sprint 2 | 2 | Anish K V
CIRRS-18 | Story | To Do | Sprint 2 | 5 | Balaji M
CIRRS-19 | Story | To Do | Sprint 2 | 5 | Balaji M
CIRRS-20 | Story | To Do | Sprint 2 | 3 | Balaji M
CIRRS-21 | Story | To Do | Sprint 2 | 8 | Balaji M
CIRRS-22 | Story | To Do | Sprint 2 | 3 | Balaji M
CIRRS-23 | Story | To Do | Sprint 2 | 5 | Balaji M
CIRRS-24 | Story | To Do | Sprint 2 | 3 | Balaji M
CIRRS-25 | Story | To Do | Sprint 2 | 3 | Balaji M
CIRRS-26 | Story | To Do | Sprint 3 | 8 | Balaji M
CIRRS-27 | Story | To Do | Sprint 3 | 5 | Balaji M
CIRRS-28 | Story | To Do | Sprint 3 | 5 | Anish K V
CIRRS-29 | Story | To Do | Sprint 3 | 5 | Anish K V
CIRRS-30 | Story | To Do | Sprint 3 | 3 | Anish K V
CIRRS-31 | Story | To Do | Sprint 3 | 5 | Anish K V
CIRRS-32 | Story | To Do | Sprint 3 | 5 | Balaji M
CIRRS-33 | Story | To Do | Sprint 3 | 5 | Balaji M
CIRRS-34 | Story | To Do | Sprint 3 | 8 | Balaji M
CIRRS-35 | Story | To Do | Sprint 3 | 8 | Balaji M
CIRRS-36 | Task | Done | Sprint 1 |  | Anish K V
CIRRS-37 | Task | Done | Sprint 1 |  | Anish K V
CIRRS-38 | Task | Done | Sprint 1 |  | Anish K V
CIRRS-39 | Task | To Do | Sprint 2 |  | Anish K V
CIRRS-40 | Task | To Do | Sprint 2 |  | Balaji M
CIRRS-41 | Task | To Do | Sprint 3 |  | Balaji M
CIRRS-42 | Bug | In Progress | Sprint 1 |  | Anish K V
CIRRS-43 | Bug | To Do | Sprint 1 |  | Anish K V
CIRRS-44 | Bug | To Do | Backlog |  | Anish K V
CIRRS-45 | Bug | To Do | Backlog |  | Balaji M
CIRRS-46 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-47 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-48 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-49 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-50 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-51 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-52 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-53 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-54 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-55 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-56 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-57 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-58 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-59 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-60 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-61 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-62 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-63 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-64 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-65 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-66 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-67 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-68 | Sub-task | In Progress | Sprint 1 |  | Anish K V
CIRRS-69 | Sub-task | In Progress | Sprint 1 |  | Anish K V
CIRRS-70 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-71 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-72 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-73 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-74 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-75 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-76 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-77 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-78 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-79 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-80 | Sub-task | To Do | Sprint 1 |  | Anish K V
CIRRS-81 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-82 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-83 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-84 | Sub-task | Done | Sprint 1 |  | Anish K V
CIRRS-85 | Sub-task | In Progress | Sprint 1 |  | Anish K V
CIRRS-90 | Sub-task | In Progress | Sprint 1 |  | Anish K V
CIRRS-86 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-87 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-88 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-89 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-105 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-100 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-99 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-106 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-91 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-95 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-97 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-98 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-93 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-108 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-102 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-96 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-103 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-107 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-109 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-110 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-111 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-112 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-113 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-114 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-115 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-116 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-117 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-118 | Sub-task | To Do | Sprint 2 |  | Balaji M
CIRRS-101 | Sub-task | To Do | Sprint 3 |  | Balaji M
CIRRS-94 | Sub-task | To Do | Sprint 3 |  | Balaji M
CIRRS-104 | Sub-task | To Do | Sprint 3 |  | Balaji M
CIRRS-92 | Sub-task | To Do | Sprint 3 |  | Balaji M
CIRRS-119 | Sub-task | To Do | Sprint 3 |  | Anish K V
CIRRS-120 | Sub-task | To Do | Sprint 3 |  | Anish K V
CIRRS-121 | Sub-task | To Do | Sprint 3 |  | Anish K V